## Review Comments
S.NO | APP NAME | SCREEN NAME | ENHANCEMENTS | PRIORITY | TYPE | NEUERUNG TECH REMARKS | BUDDHI TECHNOLOGIC REMARKS | EXPECTED DATE OF DELIVERY
1 | SUBSCRIBER | HOME PAGE | SEARCH BAR TO BE ADDED | HIGH | NEW | TO SEARCH THE DESIRED SERVICES FROM HOME PAGE | Shall add Search Bar | This Date depends on the successful completion of review of all apps and services(feature or Change would have impact on other Apps too) by the Client, and the Final To-Do List is arrived and mutually agreed upon, which would help expedite the Release Candidates.
2 | SUBSCRIBER | CONSULTATION TAB | SEARCH BAR TO BE ADDED | HIGH | NEW | TO MAKE THE SEARCH EASY | Shall add Search Bar
3 | SUBSCRIBER | CONSULTATION TAB | (a) TO DISPLAY ONLY SPECIALITIES AS DISCUSSED | HIGH | NEW | TO FOCUS ON THE TARGET POPULATION WHO REQUIRE LONG FOLLOW UP | Shall Limit the Specialities List
| SUBSCRIBER |  | (b) ADD NEUROLOGY, NEUROSURGERY, GENERAL MEDICINE, PSYCHIATRY, GEDIATRIC MEDICINE, ENDOCRINOLOGY, DENTISTRY, | HIGH | NEW |  | --DO--
4 | SUBSCRIBER | HOME CARE TAB | SEARCH BAR TO BE ADDED | HIGH | NEW | TO MAKE THE SEARCH EASY
5 | SUBSCRIBER | HOME CARE TAB | TO MENTION ONLY 1. ELDERLY CARE 2. DEMENTIA CARE 3. CRITICAL CARE AT HOME 4. NURSING ASSISTANCE AT HOME 5.HOME PHYSIOTHERAPY 6.NEURO REHABILITATION | HIGH | NEW | TO MAKE A FOCUSSED APPROACH TO NEEDED SERVICES FOR CHRONIC CARE | Shall Limit the Home Care List
6 | SUBSCRIBER | HEALTH HUB | TO ADD MEDICAL RECORDS | HIGH | NEW | REFER TO HEALTHPLIX APP. ABHA INTEGRATION WILL BE DONE TO MAINTAIN RECORDS | Shall Integrate ABHA, subject to successful accrediation with ABHA.
7 | SUBSCRIBER | HEALTH HUB | HEALTH FEEDS/SHORTS IN YOUTUBE BY DOCTORS TO BE IN HEALTHFEEDS | HIGH | NEW | THIS FEATURE IS BASED ON OUR HYPERLOCAL CONCEPT AS DISCUSSED | Shall Integrate in the Health Hub
8 | SUBSCRIBER | DIAGNOSTICS TAB | LAB TEST AT HOME (NAME TO CHANGED ) | HIGH | NEW | REFER TO APOLLO 24/7,TATA 1MG FOR LAB SERVICES | Already This feature is Present
9 | SUBSCRIBER | DIAGNOSTICS TAB | SCAN CENTRE NEAR ME (SEPARATE TAB IN HOME PAGE | HIGH | NEW |  | Already This feature is Present. Lets Scramble the Home Page to include this too.
10 | SUBSCRIBER | BOOKING | ORDER TRACKING FOR STORES /HOME CARE SERVICES | HIGH | NEW |  | Status Watch is there for ORDERS, Real-time tracking requires more 3rd party integrations. HOLD for subsequent releases. For other Internal services like Home care, Tracking would be added appropriately.
11 | SUBSCRIBER | BOOKING | TO DISPLAY PREVIOUS BOOKINGS/CONSULTATIONS | HIGH | NEW |  | Already This feature is Present
12 | SUBSCRIBER | PROFILE | NAME AGE/GENDER/ABHA NO CONTACT DETAILS | HIGH | ENHANCEMENT | REFER HEALTHPLIX AP FOR PROFILE | Already This feature is Present, except ABHA
13 | SUBSCRIBER | PROFILE | TO ADD FAMILY MEMBER/OTHER PROFILE SWITCHING TO BOOK FOR FAMILY MEMBERS/FAMILY MEMBERS ABHA NUMBER | HIGH | ENHANCEMENT | REFER HEALTHPLIX APP | Already This feature is Present in the backend, Will bring as a feature in the next release, except ABHA
14 | SUBSCRIBER | BOOKING | LOCATION/ETA FOR HOME CARE SERVICES TO BE DISPLAYED | HIGH | NEW | SIMILAR TO FOOD APPS WHICH DISPLAY ETA | Shall add this as Every service provider will use our Mobile app. Need Clarity about "Tracking Window Period"
15 | DOCTOR'S APP | PATIENT'S tab | NAME/AGE/GENDER alone to be mentioned .Remove blood group which is mentioned |  | Modify |  | Shall remove
16 | DOCTOR'S APP | OPEN PATIENT'S PROFILE PAGE | a) UNDER LAST VISITED HISTORY- REMOVE VITALS |  | Modify |  | Shall remove
17 | DOCTOR'S APP |  | b)MENTION FOLLOW UP VISIT Date & ADD BOOK APPOINTMENT ICON |  | Modify |  | Looks out of context in doctor app
18 | DOCTOR'S APP |  | c) SET REMINDER FOR MEDICINES PRESCRIBED |  | Modify |  | Not understandable. Might have backend impact.
19 | DOCTOR'S APP |  | d) PRESCRIBED TEST SHOULD BE LAB/IMAGING |  | Modify |  | Shall update
20 | DOCTOR'S APP |  | e) MENTION DOCTOR'S REFERRAL ONLY IF PRESENT |  | Modify |  | Shall update
21 | DOCTOR'S APP |  | f) REMOVE VITALS PRESCRIBED,PROCEDURES AND MENTION ONLY INSTRUCTIONS |  | Modify |  | Shall update
22 | DOCTOR'S APP | prescription tab | Doctor's original prescription to be displayed with clinic name and doctor's sign (digital sign) - Refer healthplix for example .Its in pdf format |  | Modify |  | Shall update
23 | DOCTOR'S APP | Doctor's prescription | 1.Remove symptoms-mention only vitlas |  | Modify |  | Shall remove
24 | DOCTOR'S APP | Doctor's prescription | 2.Add height and BMI |  | Modify |  | Shall add
25 | DOCTOR'S APP | Doctor's prescription | 3.Remove drug allergy |  | Modify |  | Shall remove
26 | DOCTOR'S APP | Doctor's prescription | 4.Prescription pattern-Refer apps -Healthplix,ekacare,apollo,pharmeasy |  | Modify |  | Shall refer and update
27 | DOCTOR'S APP | Doctor's prescription | 5.Add review date and digital sign |  | Modify |  | Review date is mentioned as next visit date. Will rename and add digital sign
28 | DOCTOR'S APP | Doctor's prescription -Investigations page | change pathology to labs.2.Radiology to imaging |  | Modify |  | Shall change
29 | DOCTOR'S APP | Doctor's prescription-Instruction page | Remove vitals in instructions.Change Refer specialist to refer speciality |  | Modify |  | Shall change
30 | DOCTOR'S APP | Doctor's prescriptions -review page | Vitals,chief complaints,diagnosis,Prescription lab imaging ,advise and instruction to be displayed |  | Modify |  | Not understandable.
31 | DOCTOR'S APP | Appointment tab | Remove appointment tab and replace it with healthhub.Upload reels and shorts and views viewed . |  | Modify |  | Shall add
32 | DOCTOR'S APP | Profile tab-personal details | Remove pan details.Remove mci and hpr id and shift it qualification tab |  | Modify |  | Might have impact with finance management in future. Shall remove
33 | DOCTOR'S APP | Profile tab-personal details | Remove address page |  | Modify |  | Shall remove
34 | DOCTOR'S APP | Profile tab | Remove the word Existing "in qualification page.Add tab for uploading HPR id/TNMC registration certificate |  | Modify |  | Shall update
35 | DOCTOR'S APP | Professional/business to be changed | Rename the header of this page to CLINIC DETAILS |  | Modify |  | Shall update
36 | DOCTOR'S APP | Edit clinic tab | Remove GST,Slot duration.After adding clinic mention timing below the clinic for easy review by the doctor .Add apply to all tab if timing is same for all days |  | Modify |  | If Slot is removed, appointment sequence will be collapsed. Shall remove GST and update timing view.
37 | DOCTOR'S APP | banking details | add upi id |  | Modify |  | Shall add
38 | DOCTOR'S APP | Profile page | Remove about me |  | Modify |  | About me is the promotional content for the doctor. Shall remove.
39 | DOCTOR'S APP | preferences page | rename as diagnostics labs to Diagnostic. |  | Modify |  | Shall update
40 | PHYSIOTHERAPIST LOG IN | HOME PAGE | EDIT ASSIGNED SERVICES TO" ASSIGNED PATIENTS " |  |  |  | Shall update
41 | PHYSIOTHERAPIST LOG IN | REQUESTED TAB | YOU DON’T HAVE ANY APPOINTMENT REQUEST ( TO BE CHANGED TO THIS STATEMENT) |  |  |  | Shall update
42 | PHYSIOTHERAPIST LOG IN | APPOINTMENTS TAB | YOU DON’T HAVE APPOINTMENTS- TO BE CORRECTED |  |  |  | Shall update
43 | PHYSIOTHERAPIST LOG IN | PROFILE TAB | CHANGE PRIMARY SPECIALIZATION TO "SPECIALIZATION" ONLY |  |  |  | Shall update
44 | PHYSIOTHERAPIST LOG IN | PROFILE TAB | NON FUNCTIONAL MOBILE NUMBER AND EMAIL ADDRESS OPTIONS |  |  |  | Shall update
45 | PHYSIOTHERAPIST LOG IN | SCREENING TAB | REMOVE SCREENING TAB COMPLETELY |  |  |  | Shall be removed which will result in a simple appointment checking app.
46 | DIAGONSTICS LOG IN | HOME PAGE | YOU DON’T HAVE APPOINTMENTS- TO BE CORRECTED |  |  |  | Shall update
47 | DIAGONSTICS LOG IN | ADD NEW SCREEN FOR SHOWING APPOINTMENT REQUEST | ADD NEW SCREEN FOR SHOWING APPOINTMENT REQUEST |  |  |  | Implemented in the DC web. Not under the scope of technician
48 | NURSING LOG IN | HOME PAGE | YOU DON’T HAVE APPOINTMENTS- TO BE CORRECTED |  |  |  | Shall update
49 | WEB APP |  | LOG OUT TAB TO BE ADDED |  |  |  | Logout is already present on the bottom left. (Menu)
50 | WEB APP | PROFILE | UPI ID TO BE ADDED |  |  |  | Shall update
51 | WEB APP | NURSING PROFILE | ONLY MENTION STATISTICS OVERVIEW 2.CHANGE TOTAL CUSTOMERS TO SERVICES COMPLETED |  |  |  | Unable to understand "ONLY MENTION STATISTICS OVERVIEW". 2. Shall update
52 | PHYSIOTHERAPIST LOG IN | APPOINTMENTS TAB | CHANGE CUSTOMER NAME TO PATIENT'S NAME |  |  |  | Shall update
53 | PHYSIOTHERAPIST LOG IN | PROFILE | DEGREE -REMOVE EXAMPLES MENTIONED IN BRACKET.2.REMOVE QUALIFICATION AND MENTION ONLY SPECIALIZATION3.TAB TO UPLOAD REGISTRATION CERTIFICATE |  |  |  | Need to discuss
54 | HOME CARE APP | PROFILE | UPI ID TO BE ADDED |  |  |  | Shall update
55 | HOME CARE APP | PROFILE | REMOVE ABOUT YOUR PRACTISE |  |  |  | Shall update